## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Driver | drive the truck | I Can drive the truck properly. | 1 |  | 2018-09-12
1 | SB1/US2 | Driver | receive the notification | I can receive the notification on mobile. | 1 |  | 2018-09-12
1 | SB1/US3 | Driver | call the sweeper | I can call the sweeper for receiving garbage. | 2 |  | 2018-09-12
1 | SB1/US4 | Driver | trace the location | I Can trace the location through GPS. | 1 |  | 2018-09-12
1 | SB1/US5 | Driver | search the path | I Can Search The path throgh google API. | 2 |  | 2018-09-18
1 | SB1/US6 | Driver | folllow the path | I Can follow the path through google API. | 3 |  | 2018-09-18
1 | SB1/US7 | Driver | reached the destination | I can receive the destination reached message. | 3 |  | 2018-09-18
1 | SB1/US8 | Driver | id specific | I have id to reach particular location. | 4 |  | 2018-09-18
1 | SB1/US9 | Driver | Search the nearest path | I Can search the nearest path through the google API. | 4 |  | 2018-09-18
1 | SB1/US10 | Driver | far location waiting | I Can put the farest location in waiting. | 4 |  | 2018-09-18
2 | SB2/US1 | Admin | Set the system | I Can set the system. | 1 |  | 2018-10-02
2 | SB2/US2 | Admin | fix the GSM module | I Can fix the gsm module. | 1 |  | 2018-10-02
2 | SB2/US3 | Admin | fix the GPS | I Can fix the GPS. | 2 |  | 2018-10-02
2 | SB2/US4 | Admin | fix the google api | I Can fix the google api | 3 |  | 2018-10-02
2 | SB2/US5 | Admin | fix the weight sensor | I Can fix the weight sensor so that it will tell about the. | 3 |  | 2018-10-07
2 | SB2/US6 | Admin | fix the height sensor | I Can fix the height sensor so that it will tell about height. | 4 |  | 2018-10-07
2 | SB2/US7 | Admin | update the system | I can update the system. | 4 |  | 2018-10-07
2 | SB2/US8 | Admin | fix the sms API | I Can fix the API so that driver will receive the sms. | 4 |  | 2018-10-07
2 | SB2/US9 | Admin | details of drivers | I Can keep the details of drivers. | 4 |  | 2018-10-07
2 | SB2/US10 | Admin | details of sweepers | I can keep the details of sweepers. | 4 |  | 2018-10-07
2 | SB2/US11 | Admin | details of dustbin | I Can keep the deatils of every dustbin. | 4 |  | 2018-10-07
2 | SB2/US12 | Admin | details of truck | I Can keep the deatils of every truck. | 4 |  | 2018-10-07
3 | SB3/US1 | Sweeper | called by driver | I would be called by driver. | 1 |  | 2018-10-16
3 | SB3/US2 | Sweeper | put into dustbin | I can put the garbage into dustbin. | 1 |  | 2018-10-16
3 | SB3/US3 | Sweeper | knock public | I can knock the door to the public. | 1 |  | 2018-10-23
3 | SB3/US4 | Sweeper | help the driver | I can help the driver for finding the route. | 2 |  | 2018-10-23
3 | SB3/US5 | Sweeper | take the complain | I can take the complain of public. | 2 |  | 2018-10-23
3 | SB3/US6 | Sweeper | empty the dustbin | I can empty the dustbin. | 3 |  | 2018-10-23
3 | SB3/US7 | Sweeper | details of truck driver | I can keep the details of truck driver. | 3 |  | 2018-10-23
3 | SB3/US8 | Sweeper | detail of his own truck | I can keep the detail of his own truck. | 4 |  | 2018-10-23
4 | SB4/US1 | Public | keep the address of admin | I can keep the address of admin. | 1 |  | 2019-01-15
4 | SB4/US2 | Public | complain the public | I can complain to the public. | 2 |  | 2019-01-15
4 | SB4/US3 | Public | fill the garbage | I can fill the garbage into dustbin. | 3 |  | 2019-01-15
4 | SB4/US4 | Public | call the admin | I can call the admin regarding garbage. | 4 |  | 2019-01-15
4 | SB4/US5 | Public | call the driver | I can call the driver | 4 |  | 2019-01-15

## SprintBacklog1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - IOT BASED DUSTBIN
SB1/US1 | Drive the truck | SB1/D1/T1 | Design the GUI | Varshal Arora | In progress | 2018-09-12
|  | SB1/D1/T2 | Coding | Varshal Arora | In progress | 2018-09-12
|  | SB1/D1/T3 | Connect with Database | Varshal Arora | In progress | 2018-09-12
SB1/US2 | Receive the notification | SB1/D2/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-09-12
|  | SB1/D2/T2 | Coding | Vipin Yadav | Not Started | 2018-09-12
|  | SB1/D2/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-09-12
SB1/US3 | Call the sweeper | SB1/D3/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-09-18
|  | SB1/D3/T2 | Coding | Vipin Yadav | Not Started | 2018-09-18
|  | SB1/D3/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-09-18
SB1/US4 | Trace the location | SB1/D4/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-09-18
|  | SB1/D4/T2 | Coding | Vipin Yadav | Not Started | 2018-09-18
|  | SB1/D4/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-09-18
SB1/US5 | Search the path | SB1/D5/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-09-18
|  | SB1/D5/T2 | Coding | Vipin Yadav | Not Started | 2018-09-18
|  | SB1/D5/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-09-18
SB1/US6 | Folllow the path | SB1/D6/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-09-18
|  | SB1/D6/T2 | Coding | Vipin Yadav | Not Started | 2018-09-18
|  | SB1/D6/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-09-18
SB1/US7 | Reached the destination | SB1/D7/T1 | Design the GUI | Varshal Arora | Not Started | 2018-09-18
|  | SB1/D7/T2 | Coding | Varshal Arora | Not Started | 2018-09-18
|  | SB1/D7/T3 | Connect with Database | Varshal Arora | Not Started | 2018-09-18
SB1/US8 | ID specific | SB1/D8/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-09-18
|  | SB1/D8/T2 | Coding | Vipin Yadav | Not Started | 2018-09-18
|  | SB1/D8/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-09-18
SB1/US9 | Search the nearest path | SB1/D9/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-09-18
|  | SB1/D9/T2 | Coding | Vipin Yadav | Not Started | 2018-09-18
|  | SB1/D9/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-09-18
SB1/US10 | Far location waiting | SB1/D10/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-09-18
|  | SB1/D10/T2 | Coding | Vipin Yadav | Not Started | 2018-09-18
|  | SB1/D10/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-09-18

## SB HOURS 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup | 6
|  | Search about components required | 8
|  | Purchase component from Market | 4
|  | Develop the hardware | 8
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application | 4
|  | search paint application | 6
|  | search video making application | 4
|  | search audio recording applications | 4
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials | 6
|  | Study tutorials | 8
|  | start with Basics of Java | 4
|  | start with Basics of Java | 6
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of Java | 8
|  | start with Basics of Java | 4
|  | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
|  | Debug the code | 4
|  | Debug the code | 4
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. | 4
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 6
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
|  | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | 4
|  | Use different applications on the virtual screen | 4
|  | Check the changes made at the virtual screen | 6
|  | Checking if it is working effectively with the laptop and not damaged | 6
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | 8
|  | Prepare all software deliverables | 6
|  | Prepare a hardware & software guide | 8
|  | Prepare a user manual & guide for the users | 6
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project | 6
|  | Project demonstration | 8
|  | Project demonstration | 4
|  | Project to be operated by different users | 4

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-12 | 30 | 30
2018-09-18 | 0 | 30
Days

## SprintBacklog2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - IOT BASED DUSTBIN
SB2/US1 | Set the system | SB2/D1/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-02
|  | SB2/D1/T2 | Coding | Vipin Yadav | Not Started | 2018-10-02
|  | SB2/D1/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-02
SB2/US2 | Fix the GSM module | SB2/D2/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-02
|  | SB2/D2/T2 | Coding | Vipin Yadav | Not Started | 2018-10-02
|  | SB2/D2/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-02
SB2/US3 | Fix the GPS | SB2/D3/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-02
|  | SB2/D3/T2 | Coding | Vipin Yadav | Not Started | 2018-10-02
|  | SB2/D3/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-02
SB2/US4 | Fix the google api | SB2/D4/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-02
|  | SB2/D4/T2 | Coding | Vipin Yadav | Not Started | 2018-10-02
|  | SB2/D4/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-02
SB2/US5 | Fix the weight sensor | SB2/D5/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-02
|  | SB2/D5/T2 | Coding | Vipin Yadav | Not Started | 2018-10-02
|  | SB2/D5/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-02
SB2/US6 | Fix the height sensor | SB2/D6/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-02
|  | SB2/D6/T2 | Coding | Vipin Yadav | Not Started | 2018-10-02
|  | SB2/D6/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-02
SB2/US7 | Update the system | SB2/D7/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-07
|  | SB2/D7/T2 | Coding | Vipin Yadav | Not Started | 2018-10-07
|  | SB2/D7/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-07
SB2/US8 | Fix the sms API | SB2/D8/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-07
|  | SB2/D8/T2 | Coding | Vipin Yadav | Not Started | 2018-10-07
|  | SB2/D8/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-07
SB2/US9 | Details of drivers | SB2/D9/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-07
|  | SB2/D9/T2 | Coding | Vipin Yadav | Not Started | 2018-10-07
|  | SB2/D9/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-07
SB2/US10 | Details of sweepers | SB2/D10/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-07
|  | SB2/D10/T2 | Coding | Vipin Yadav | Not Started | 2018-10-07
|  | SB2/D10/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-07
SB2/US11 | Details of dustbin | SB2/D11/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-07
|  | SB2/D11/T2 | Coding | Vipin Yadav | Not Started | 2018-10-07
|  | SB2/D11/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-07
SB2/US12 | Details of truck | SB2/D12/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-07
|  | SB2/D12/T2 | Coding | Vipin Yadav | Not Started | 2018-10-07
|  | SB2/D12/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-07

## SB HOURS 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup | 6
|  | Search about components required | 8
|  | Purchase component from Market | 4
|  | Develop the hardware | 8
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application | 4
|  | search paint application | 6
|  | search video making application | 4
|  | search audio recording applications | 4
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials | 6
|  | Study tutorials | 8
|  | start with Basics of Java | 4
|  | start with Basics of Java | 6
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of Java | 8
|  | start with Basics of Java | 4
|  | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
|  | Debug the code | 4
|  | Debug the code | 4
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. | 4
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 6
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
|  | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | 4
|  | Use different applications on the virtual screen | 4
|  | Check the changes made at the virtual screen | 6
|  | Checking if it is working effectively with the laptop and not damaged | 6
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | 8
|  | Prepare all software deliverables | 6
|  | Prepare a hardware & software guide | 8
|  | Prepare a user manual & guide for the users | 6
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project | 6
|  | Project demonstration | 8
|  | Project demonstration | 4
|  | Project to be operated by different users | 4

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-10-02 | 36 | 36
2018-10-07 | 0 | 36
Days

## SprintBacklog3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - IOT BASED DUSTBIN
SB3/US1 | Called by driver | SB3/D1/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-16
|  | SB3/D1/T2 | Coding | Vipin Yadav | Not Started | 2018-10-16
|  | SB3/D1/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-16
SB3/US2 | Put into dustbin | SB3/D2/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-16
|  | SB3/D2/T2 | Coding | Vipin Yadav | Not Started | 2018-10-16
|  | SB3/D2/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-16
SB3/US3 | Knock public | SB3/D3/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-16
|  | SB3/D3/T2 | Coding | Vipin Yadav | Not Started | 2018-10-16
|  | SB3/D3/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-16
SB3/US4 | Help the driver | SB3/D4/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-16
|  | SB3/D4/T2 | Coding | Vipin Yadav | Not Started | 2018-10-16
|  | SB3/D4/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-16
SB3/US5 | Take the complain | SB3/D5/T1 | Design the GUI | Vipin Yadav | Not Started | 2018-10-23
|  | SB3/D5/T2 | Coding | Vipin Yadav | Not Started | 2018-10-23
|  | SB3/D5/T3 | Connect with Database | Vipin Yadav | Not Started | 2018-10-23
SB3/US6 | Empty the dustbin | SB3/D6/T1 | Design the GUI | Varshal Arora | Not Started | 2018-10-23
|  | SB3/D6/T2 | Coding | Varshal Arora | Not Started | 2018-10-23
|  | SB3/D6/T3 | Connect with Database | Varshal Arora | Not Started | 2018-10-23
SB3/US7 | Details of truck driver | SB3/D7/T1 | Design the GUI | Varshal Arora | Not Started | 2018-10-23
|  | SB3/D7/T2 | Coding | Varshal Arora | Not Started | 2018-10-23
|  | SB3/D7/T3 | Connect with Database | Varshal Arora | Not Started | 2018-10-23
SB3/US8 | Detail of his own truck | SB3/D8/T1 | Design the GUI | Varshal Arora | Not Started | 2018-10-23
|  | SB3/D8/T2 | Coding | Varshal Arora | Not Started | 2018-10-23
|  | SB3/D8/T3 | Connect with Database | Varshal Arora | Not Started | 2018-10-23

## SB HOURS 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup | 6
|  | Search about components required | 8
|  | Purchase component from Market | 4
|  | Develop the hardware | 8
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application | 4
|  | search paint application | 6
|  | search video making application | 4
|  | search audio recording applications | 4
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials | 6
|  | Study tutorials | 8
|  | start with Basics of Java | 4
|  | start with Basics of Java | 6
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of Java | 8
|  | start with Basics of Java | 4
|  | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
|  | Debug the code | 4
|  | Debug the code | 4
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. | 4
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 6
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
|  | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | 4
|  | Use different applications on the virtual screen | 4
|  | Check the changes made at the virtual screen | 6
|  | Checking if it is working effectively with the laptop and not damaged | 6
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | 8
|  | Prepare all software deliverables | 6
|  | Prepare a hardware & software guide | 8
|  | Prepare a user manual & guide for the users | 6
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project | 6
|  | Project demonstration | 8
|  | Project demonstration | 4
|  | Project to be operated by different users | 4

## SB BD Ch03
Spring Backlog 03 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-10-16 | 24 | 24
2018-10-23 | 0 | 24
Days

## SprintBacklog4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - IOT BASED DUSTBIN
SB4/US1 | Keep the address of admin | SB4/D1/T1 | Design the GUI | Varshal Arora | Not Started | 2019-01-10
|  | SB4/D1/T2 | Coding | Varshal Arora | Not Started | 2019-01-10
|  | SB4/D1/T3 | Connect with Database | Varshal Arora | Not Started | 2019-01-10
SB4/US2 | Complain the public | SB4/D2/T1 | Design the GUI | Vipin Yadav | Not Started | 2019-01-10
|  | SB4/D2/T2 | Coding | Vipin Yadav | Not Started | 2019-01-10
|  | SB4/D2/T3 | Connect with Database | Vipin Yadav | Not Started | 2019-01-10
SB4/US3 | Fill the garbage | SB4/D3/T1 | Design the GUI | Varshal Arora | Not Started | 2019-01-15
|  | SB4/D3/T2 | Coding | Varshal Arora | Not Started | 2019-01-15
|  | SB4/D3/T3 | Connect with Database | Varshal Arora | Not Started | 2019-01-15
SB4/US4 | Call the admin | SB4/D4/T1 | Design the GUI | Varshal Arora | Not Started | 2019-01-15
|  | SB4/D4/T2 | Coding | Varshal Arora | Not Started | 2019-01-15
|  | SB4/D4/T3 | Connect with Database | Varshal Arora | Not Started | 2019-01-15
SB4/US5 | Call the driver | SB4/D5/T1 | Design the GUI | Varshal Arora | Not Started | 2019-01-15
|  | SB4/D5/T2 | Coding | Varshal Arora | Not Started | 2019-01-15
|  | SB4/D5/T3 | Connect with Database | Varshal Arora | Not Started | 2019-01-15

## SB HOURS 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup | 6
|  | Search about components required | 8
|  | Purchase component from Market | 4
|  | Develop the hardware | 8
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application | 4
|  | search paint application | 6
|  | search video making application | 4
|  | search audio recording applications | 4
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials | 6
|  | Study tutorials | 8
|  | start with Basics of Java | 4
|  | start with Basics of Java | 6
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of Java | 8
|  | start with Basics of Java | 4
|  | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
|  | Debug the code | 4
|  | Debug the code | 4
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. | 4
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 6
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
|  | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | 4
|  | Use different applications on the virtual screen | 4
|  | Check the changes made at the virtual screen | 6
|  | Checking if it is working effectively with the laptop and not damaged | 6
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | 8
|  | Prepare all software deliverables | 6
|  | Prepare a hardware & software guide | 8
|  | Prepare a user manual & guide for the users | 6
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project | 6
|  | Project demonstration | 8
|  | Project demonstration | 4
|  | Project to be operated by different users | 4

## SB BD Ch04
Spring Backlog 04 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2019-01-10 | 15 | 15
2019-01-15 | 0 | 15
Days